## Slide 1
Values
Strategies
Vision
Trust
Respect
Teamwork
Commitment
Safety
Community
Engagement
Management Systems
Patient
Centric
One
Team
Financial
Stewardship
Mission
Framework
for continuous
improvement
We exceed the
expectations of our
unique Island community
We serve our community before, during and after
an emergency
DRAFT

## Slide 2: 1. Community engagement strategy
A. Establish community engagement programs | Lead | Goal
Identify community stakeholders Lights and Sirens Newsletter - routine updates, once a quarter Establish 2018 Engagement Plan Establish EMS newspaper(s) column for time sensitive updates Make performance metrics public - signage on building, etc. Communicate benefits for residents Utilize patient stories to focus our work Determine frequency and topics for Town Halls - strong interest Explore the use of social media Ask community members to volunteer as a patient for training Open house - interest once in a while |  | 
#1 PRIORITY
✔️
✔️
‘A’ task
‘B’ task
B. Explore Collaborative Associate Opportunities | Lead | Goal
North Region EMS SJI fire district Orcas fire/EMS Lopez fire/EMS Shaw fire/EMS Airlift NW and Island Air Sheriff’s office Peace Health Community associations |  | 
#2 PRIORITY
✔️
✔️
✔️
✔️
✔️
✔️
✔️
✔️

## Slide 3: 2. Patient centric strategy
EMS capabilities are often only ’seen’ when the team is onsite providing advanced or basic life support.
In addition to the critically important onsite work there is a great deal of activity and resources dedicated to before and after an incident, ensuring each 911 call is patient centric and care is efficiently and effectively provided.
The strategies and tactics associated with ‘before-during-after’ a call are being reviewed in depth with respect to the cost/value added of each service.

## Slide 4: 2. Patient centric strategy
B. During an event
Advanced Life Support
Patient engagement Family engagement Utilize ALS training Assist to ER Fit for jail blood draw
Basic Life Support
Patient engagement Family engagement Utilize BLS training Assist to ER Assist ALS as needed
A. Before an event
ALS training initial 3300 hrs.
UW Med Program OTEP 1/ mon. Advanced wilderness Marine Rescue - WA State Infectious disease ACLS & ACLS XP PALS Neonatal Rescue ATLS SAR Critical Certifications
BLS training initial 250 hrs.
Initial EMT course OTEP 2/mon. WEMT Marine Rescue - WA State CPR plus AED ACLS PEARS PHTLS SAR
C. After an event
Advanced Life Support
Run reviews Quality Assurance Quality Improvement Remedial training Death notification Referral for EMS resources Referral for other services: --DVSAS, CPS, APS, Mental --Health, senior services Patient follow-up
Basic Life Support
Run Reviews Quality Assurance Quality Improvement Remedial training Referral for EMS resources Referral for other services Patient follow-up
#1 PRIORITY

## Slide 5: 2. Patient centric strategy - continued
B. During an event - con.
ALS Skills
All BLS plus ALS Advanced airway Flutter valves IV - 10 Cardioversion Advanced medications
BLS Skills
CPR AED Wound care IV tech Splinting Radio communications Choking Driving ambulance Advanced skills preparation BLS approved medications
A. Before an event - con.
ALS & BLS drills
Active shooter Skills and abilities MCI Rescue SAR Regulatory checks
ALS & BLS classes
FEMA ICS 100, 200, 700 WA State Paramedic WA State EMT Rig checks
C. After an event - con.
ALS & BLS patient assistance
Family & friend referrals Child care Pet and animal care Transportation arrangements Safety hazards House marker installation

## Slide 6: 2. Patient centric strategy - continued
B. During an event - con.
Education & Outreach
1st Aid during events Fall prevention 1/1
A. Before an event - con.
Education - classes “in-house”
CPR and 1st aid Wilderness 1st Responder, Aid Wilderness EMT module Infectious disease Safe sitter Advanced Cardio Life Support Pediatric Advanced Life Experienced provider PEARS and PHTLS Poison Board and Box
Outreach
Kid’s don’t float program Every 15 minutes; driving Fall prevention Blood pressure clinic Safety Fair Touch a Truck Car seats and bike helmets
C. After an event - con.
Education & Outreach
BP Clinic follow-up Safe Sitter 1/1 Fall prevention 1/1 Car seats and bike helmets

## Slide 7: 3. One team strategy
B. Align organization structure with Framework | Lead | Measure
Establish a structure renewal team Identify current structure challenges and opportunities Identify current roles and responsibilities Align functions with strategic framework Establish draft organization structure alternatives Align personnel with selected alternative Engage all stakeholders, communicate |  | 
A. Continually enhance governance effectiveness | Lead | Measure
Align work with Strategic Framework - build into annual work plan Establish governance role, management responsibility compact Commissioner position descriptions, annual evaluations New commissioner orientation Commissioner continuous learning program |  | 
C. Align roles and responsibilities | Lead | Measure
Superintendent, Chief, opns/admin staff, med staff, medics, EMT’s, LT’s Establish position descriptions Train and coach Conduct 3 month evaluations in roles Prepare succession plans |  | 
‘A’ task
‘B’ task
#2 PRIORITY
#1 PRIORITY
#1 PRIORITY
✔️
✔️
✔️
✔️

## Slide 8: 3. One team strategy
D. Enhance EMT engagement - one team | Lead | Measure
Renew organization structure, with EMT input Establish varied interests, needs and aspirations of each EMT Determine how to build upon diversity to create a collaborate team Establish appropriate resources to enhance and retain the EMT team Develop a program to recruit new EMT’s |  | 
E. Ensure SJI EMS is a competitive, supportive, fun place to work | Lead | Measure
Competitive compensation Reasonable work hours and work shifts Competitive benefits Clear roles and responsibilities Selection policies Evaluation policies Recognition policies Accountability policies Retention policies Training policies Coaching opportunities Safety policy adherence Burn out recognition and support |  | 
‘A’ task
‘B’ task
#1 PRIORITY
#2 PRIORITY
Task priorities TBD

## Slide 9: 4. Management system strategy
B. Implement the strategic framework | Lead | Measure
Prepare visual tools; posters, work area placards, badges? Utilize the framework routinely Make critical decisions with framework “in-hand” Embed framework components in all policies and procedures Support embedding values with training |  | 
A. Support change | Lead | Measure
Be clear about the need Understand the barriers Identify the opportunities Prioritize the work Pick the low hanging fruit Deploy learnings to other priorities |  | 
C. Enhance internal communication effectiveness | Lead | Measure
Determine communication challenges and opportunities Establish a communication policy Utilize the policy routinely |  | 
‘A’ task
‘B’ task
#1 PRIORITY
#2 PRIORITY
#1 PRIORITY

## Slide 10: 4. Management system strategy - cont.
D. Renew critical policies and procedures | Lead | Measure
Incident Command System Contingency planning Disaster preparedness Compliance policies Administration policies |  | 
E. Establish tactics, goals, objectives | Lead | Time
Review and finalize tactics for each strategy Establish responsibility, goals and objectives for each strategy Establish performance goals and objectives Develop a simple, high level performance dashboard Provide dashboard as a key Board oversight and support tool Go public with you measures and performance |  | 
‘A’ task
‘B’ task
#3 PRIORITY
#1 PRIORITY

## Slide 11: 5. Financial stewardship strategy
A. Enhance financial reporting system | Lead | Measure
2017 Budget format for monthly and quarterly reporting - complete Address reconciliation issues with County and State |  | 
B. Optimize financial partnership | Lead | Measure
Optimize financial partnership Develop performance metrics Establish routine performance reviews |  | 
C. Pursue revenue enhancements | Lead | Measure
Continue aggressive pursuit of grant programs Other revenue sources Audit billable calls Ground Emergency Medical Transport reimbursement opportunities Community Paramedicine program funding |  | 
‘A’ task
‘B’ task
#1 PRIORITY
#3 PRIORITY
#3 PRIORITY

## Slide 12: 5. Financial stewardship strategy - cont.
D. Pursue operating expense efficiencies | Lead | Measure
Prevent expense creep Labor agreement Civil Investigative Demand management Legal and consulting fees - review contracts and value added Retirement system review - transition to LEAF Conduct an expense comparison to like organizations/services |  | 
E. Pursue non-operating efficiencies | Lead | measure
Establish operating contingency Accounts receivable - summarize history, current state, expectations Develop five year capital plan Inter Island Medical Center Building - keep pressure on to sell Educate the staff on financial statements Establish the strategic framework resource needs, wants, nice-to-have |  | 
‘A’ task
‘B’ task
#1 PRIORITY
#1 PRIORITY

## Slide 13: Framework priorities summary #1
Enhance community engagement
Align organization structure with Framework
Ensure ‘One Team’ EMT engagement
Clarify roles, responsibilities, accountability
Set training priorities, ensure program effectiveness
Embed values in daily work
Establish patient centric strategic priorities
Establish financial reserve
Prevent expense creep

## Slide 14: Framework priorities summary #2
Align Framework and budget
Establish operating contingency
Maximize revenues, minimize costs, build reserves
Pursue collaborative association opportunities
Align governance work with Framework
Prioritize policy renewal work

## Slide 15: Framework goals - being developed
SJI EMS Operational Key Performance Indicators
SJC EMS Key Performance Indicators
Education and training
Financial performance

## Slide 16: EMS Dashboard - will be developed
Goal | Target | Time | Trend
Objective | Target | Time | Trend

## Slide 17
Orca perspective of EMS organization ...
Critical
Jan 2016
Stable
Aug 2016
Healthy
Aug 2017
Really Good/Great
To Exceptional
2017-2020
--------- Dedicated ---------
-- Committed --
Demonstrated during very demanding period
Shown during planning process

## Slide 18
Thanks you for your input
Tom Van Dawark
Orca Partners LLC
206-786-1127
tom@orcapartnersllc.com

## Slide 19
Framework report format
Introduction; Chief and Board Chair
About us
Planning process, purpose and objectives
Where we are currently; challenges and opportunities
Where we’re going; Vision and Mission
How we’re going to get there; Strategies and Values
How we measure; Goals, Objectives and Dashboard
Resource requirements; Budget, Capital, Reserves
Appendices